## Slide 2: Storyboard Guidelines
All projects are different but there are standard tools that benefit each project
Include your own versions of all the slides shown in this sample storyboard (unless listed as optional)
Add additional slides based on your project
Include supporting slides in the Appendix
Remember to add your summary of the results of using each tool in the “Key Learning” space

## Slide 3: Executive Summary—A3

## Slide 4: Define Phase

## Slide 5: Project Charter

## Slide 6: SIPOC
Key Learning: Patient is the “thing” moving through the process.

## Slide 7: Voice of the Customer
Key Learning: Patients were concerned with delays in hospitalization.

## Slide 8: Swimlane Map
Key Learning: Decisions and rework fall to the Hospitalist.

## Slide 9: Measure Phase

## Slide 10: Data Collection Plan
Key Learning: Data Collection uncovered multiple disparities in the process.

## Slide 11: Baseline of Project Y
Key Learning: The longest mean time to hospitalize a patient is in the 00:00 to 06:00 shift.

## Slide 12: Analyze Phase

## Slide 13: Fishbone Diagram
Key Learning: Brief Orders have been prioritized as the main area of improvement.

## Slide 14: 5 Whys (optional)
Key Learning: Potential improvement to have workups done earlier.

## Slide 15: Root Cause Confirmation
Key Learning: Data shows verifies all 3 root causes (see next slide for charts).

## Slide 16: Verification Visuals (if available)
Key Learning: (see previous slide for corresponding root cause hypotheses)

## Slide 17: Improve Phase

## Slide 18: Solution Selector
Key Learning: It was not feasible to adjust staffing so the team focused first on utilization of brief orders for hospitalization.

## Slide 19: Time Chart – Before & After
Key Learning: Using brief orders for hospitalizations reduced time from request of hospitalization to PSO/Brief Orders from 104 minutes to 69 minutes—a 34% improvement in the average.

## Slide 20: Monitoring & Response Plan
Key Learning: To sustain success with Brief Orders, it will take monitoring from the team to ensure utilization of Brief Orders for hospitalizations.

## Slide 21: Project Sign-Off

## Slide 22: Appendix